## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 30 April 2023
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Person
1 | Reservoirs: Pre-loads | 50101003091/ 50101003111 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 21 | 73481277 | 59561871 | 26084733.64 | 47685250 | -33477137.36 | -56.2057 | Construction | Construction | Hard rock | Heavy excavation machinery . | Mr Steyn
2 | Rawsonville WwTW: Extension of WwTW (0,24 Ml/day) | 50101003281 | Town: Rawsonville Wards: 19,20 | 27000000 | 27000000 | 20255502 | 27000000 | -6744498 | -24.9796 | Construction | Construction | Ground water | Pumping og ground water . | Mr Steyn
3 | Transhex:Electrical Reticulation | 50101002431 | Town: Worcester. Wards: 18 | 15000000 | 15000000 | 2074713.06 | 12016765 | -12925286.94 | -86.1686 | BV899/2021 awarded | Construction | N/A | N/A | Mr Beneke
4 | Upgrading of Sewer Network: External Loan | 50101003381 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 21 | 15000000 | 15000000 | 9894149.41 | 8884302 | -5105850.59 | -34.039 | Construction | Construction | None | N/A | Mr Pekeur
5 | Supply and Installation of Load Shedding Solution and Solar PV | 50101006481 | Town: All Wards: 1 to 21 | 13420000 | 782500 | 182500 | 782500 | -600000 | -76.6773 | Engineering consultant will complete study to suggest load sheding solutions for each of 43 BVM buildings by 28 February 2023. Following that tender specifications should be complete by 31 March 2023 to enable procurement. | Preliminary study almost complete | Studies into installing small scale generation at the WWTW indicated that it would be wrong location as the substation feeds from ESKOM and can't feed into BVM's grid. It was decided to focus on business continuity for BVM office buildings, and a new study is being conducted. | New study is almost complete. Procurement will follow the study. | Mr Smal
6 | ICT - Computer Equipment | 50101004661 | Town: All Wards: 1 to 21 | 12000000 | 14340143 | 13495013.92 | 9174943 | -845129.08 | -5.8934 | Equipment currently being delivered | Equipment currently being delivered | N/A | N/A | Mr Solomon
7 | Alternative Electricity Supply Zwelethemba | 50101002231 | Town: Worcester. Wards: 8, 16, 17, 18 | 10000000 | 11800000 |  | 8000000 | -11800000 | -100 | BV970/2022 Tender to be advertised closing date 02/09/2022. Tender awarded. Within appeal period | Contract awarded | N/A | N/A | Mr Beneke
8 | Altona new Electrical Substation | 50101002121 | Town: Worcester. Wards: 5 | 10000000 | 10000000 | 9714510.56 | 10000000 | -285489.44 | -2.8549 | Practical Completion. | Practical Completion. | N/A | N/A | Mr Beneke
9 | De Doorns Water Purification Works : Augmentation of DAF Unit (MIG funding) | 50101003201 | Town: De Doorns Wards: 2 | 7773398 | 0 |  | 0 | 0 | #VALUE! | Preliminary investigation | Preliminary investigation | Project to be posponed until the 2023/2024 FY | Project to be posponed until the 2023/2024 FY | Mr Steyn
10 | 66KV Ripple Control | 50101002241 | Town: All Wards: 1 to 21 | 6900000 | 0 |  | 0 | 0 | #VALUE! | Tender cancelled | Spesification | Project to be posponed until the 2023/2024 FY | Project to be posponed until the 2023/2024 FY | Mr Beneke
Totals |  |  |  | 190574675 | 153484514 | 81701122.59 | 123543760 | -71783391.41 | -46.7691
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)