## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 31 August 2020
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Directorate
1 | Transhex: Electrical Reticulation | 50101000041 | Town: Worcester. Wards: 18 | 22097000 | 22097000 |  | 0 | -22097000 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. BV 852/2019 Delivery towards end of September 2020 | Construction |  |  | Technical Services
2 | Reservoir: Pre-loads | 50102154361 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 12053101 | 12053101 | 661547.7 | 0 | -11391553.3 | -94.5114 | Consulting Engineer (WSP Group) and Environmental Consultant (GNE) are appointed. | Design and Environmental Assesment | Environmental Authorization (EA) | Monitoring of EA process. | Technical Services
3 | Transhex: New Bus Route (Local Distributor Class 4) | 50101000411 | Town: Worcester. Wards: 18 | 11646365 | 11646365 |  | 0 | -11646365 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
4 | Transhex: External Stormwater pipeline | 50101000531 | Town: Worcester. Wards: 18 | 6948409 | 6948409 |  | 0 | -6948409 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
5 | Transhex: Water Reticulation | 50101000071 | Town: Worcester. Wards: 18 | 6000000 | 6000000 |  | 0 | -6000000 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
6 | Transhex: Sewer Reticulation | 50101000141 | Town: Worcester. Wards: 18 | 6000000 | 6000000 |  | 0 | -6000000 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
7 | Transhex:Roads | 50101000381 | Town: Worcester. Wards: 18 | 6000000 | 6000000 |  | 0 | -6000000 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
8 | Transhex: Stormwater | 50101000511 | Town: Worcester. Wards: 18 | 6000000 | 6000000 |  | 0 | -6000000 | -100 | Western Cape Department of Public Works is responsible for implementation of Housing Development at Tranhex. | Construction |  |  | Technical Services
9 | Electricity: Cherry Picker vehicles | 50101003861 | Town: All Wards: 1 to 21 | 3860114 | 3860114 |  | 0 | -3860114 | -100 | Tender to be re-advertise expected delivery end April 2021 | Planning and design | None |  | Technical Services
10 | Jet Vac truck | 50101000181 | Town: All Wards: 1 to 21 | 3500000 | 3500000 |  | 0 | -3500000 | -100 | Contract awarded. Delivery towards end of August 2020. | Construction | None |  | Technical Services
Totals |  |  |  | 84104989 | 84104989 | 661547.7 | 0 | -83443441.3 | -99.2134
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)