## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 31 December 2021
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges.
1 | Transhex: Electrical Reticulation | 50101000041 | Town: Worcester. Wards: 18 | 21000000 | 21000000 | 496421 | 4000000 | -20503579 | -97.6361 | Bid BV899/2021 . Tenders received. Bid evaluation of tenders | Procurement | None | N/A
2 | Resealing of Municipal Roads - Worcester | 50101000451 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 21 | 25776248 | 19526091 |  | 6000000 | -19526091 | -100 | Bid BV 916/2021 Resurfacing of Municipal roads for the Period ending 30 June 2024, advertised Friday, 30th of July 2021. Closing date Friday, 3rd of September 2021. Anticipated commencement date January 2022. | Procurement | None | N/A
3 | Zwelethemba - New Swimming Pool | 50101001271 | Town: Worcester. Wards: 8, 16, 17, 18 | 15500000 | 15500000 | 14296247.79 | 14500000 | -1203752.21 | -7.7661 | Contract BV 825/2021: Construction of swimming pool facility at Zweletemba awarded to Murray & Dickson (Pty) Ltd | Construction | None | N/A
4 | Erosion Protection of Hex River : Phase 2 | 50101000521 | Town: Worcester. Wards: 8, 16, 17, 18 | 3150000 | 7828081 | 6859747.48 | 3914040 | -968333.52 | -12.37 | Contract BV 913/2021: Erosion Protection at Hex River, Zweletemba: Phase 1, awarded to Martin & East (Pty) Ltd | Construction | None | N/A
5 | Rawsonville : Extension of WwTW (0,24 Ml/day) | 50101000411 | Town: Rawsonville Wards: 19,20 | 6293742 | 6296742 | 939832.35 | 1296742 | -5356909.65 | -85.0743 | Bids BV 915/2021 (Civils & Structural) & BV 926/2021 (Mech & Elec) Upgrading of Rawsonville WwTW, advertised 27 August 2021 and 3 September 2021, respectively. Closing date of tenders Friday, 1st of October 2021 and 8 October 2021, respectively. Anticipated commencement date January 2022. | Procurement | None | N/A
6 | Upgrading of gravel roads : Ward 12 | 50102150051 | Town: Worcester. Wards:12 |  | 6250157 | 6066743.38 | 4000000 | -183413.62 | -2.9345 | Contract BV 823/2021: Upgrading of gravel roads at Avian Park, awarded to JVZ Construction (Pty) Ltd. Anticipated commencement date 16 August 2021, completion period 20 weeks, completion toward end of January 2022. | Construction | None | N/A
7 | Traffic Circles: (High and Louis Lange) | 50101001171 | Town: Worcester. Wards: 8 | 6000000 | 6000000 |  | 0 | -6000000 | -100 | Bid BV 929/2021 : Professional Services for the construction of traffic circle at High and Louis Lange Streets, advertized 3rd September 2021. Closing date of tender Friday8 October 2021. Anticipated commencement date of construction March 2022. | Procurement | None | N/A
8 | Altona new Electrical Substation | 50101000091 | Town: Worcester. Wards: 12 | 6000000 | 7300000 | 177500 | 1300000 | -7122500 | -97.5685 | Bid BV900/2021 . Tender adjudicated, in proses. | Construction | None | N/A
9 | Esselen Park : Replacement of fence perimeter | 50101001301 | Town: Worcester. Wards: 9 | 6000000 | 5000000 |  | 2000000 | -5000000 | -100 | Tender in proses. Tender were advertise Friday 30 July 2021. | Advertising | None | N/A
10 | Refurbishment of electrical system | 50101003361 | Town: All Wards: 1 to 21 | 4500000 | 4409135 | 921444.6 | 1554566 | -3487690.4 | -79.1015 | Tender in the planning proses. | Planning | None | N/A
Totals |  |  |  | 94219990 | 99110206 | 29757936.6 | 38565348 | -69352269.4 | -69.9749
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)