## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 31 January 2020
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Official
1 | Worcester : Material Recovery Facility (MIG Counter funding) | 50101002651 | Town: Worcester. Wards: 5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 16979604 | 16979604 | 14022194.6 | 9508576 | -2957409.4 | -17.4174 | Construction commenced on 28 May 2019. Completion towards end of January 2020. | Construction | None to date. | N/A | Mr Steyn
2 | TRANSHEX - Water Reticulation | 50101002581 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 8400000 | -15000000 | -100 | Construction | Construction | None to date. | N/A | Mr Steyn
3 | TRANSHEX - Sewer Reticulation | 50101002601 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 8400000 | -15000000 | -100 | Construction | Construction | None to date. | N/A | Mr Steyn
4 | TRANSHEX - Roads | 50101002761 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 8400000 | -15000000 | -100 | Construction | Construction | None to date. | N/A | Mr Steyn
5 | TRANSHEX - Stormwater | 50101002921 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 8400000 | -15000000 | -100 | Construction | Construction | None to date. | N/A | Mr Steyn
6 | Pre-loads Reservoir | 50102154361 | Town: Worcester. Wards: 5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 10652819 | 10652819 | 15835 | 5965581 | -10636984 | -99.8514 | BID BV 816/2019 Profesional Services for the Construction of 20 ML Reservoir at Pre Loads | Advertized 6 December 2019 | Time period for design and construction phase. | Fast track of procurement process, if posible. | Mr Steyn
7 | Transhex : Electrical Reticulation | 50101002531 | Town: Worcester. Wards: 18 | 10000000 | 10000000 | 1595989.66 | 5600000 | -8404010.34 | -84.0401 | Tender BV 852/2019 closed on 24/01/2020 -Bussy with the evaluation of Tender. | Tender stage | N/A | N/A | Mr Beneke
8 | De Doorns Water Purification Works : Augmentation of DAF Unit | 50101003571 | Town: Worcester. Wards: 2 ,3,4 | 7108259 | 7108259 |  | 3980626 | -7108259 | -100 | Draft specifications for the appointment of Consulting Engineers for the design and contract administration. | Specifications | Time period for design and construction phase. | Fast track of procurement process, if posible. | Mr Steyn
9 | Zweletemba - New Swimming Bath | 50101004421 | Town: Worcester. Wards: 8, 16-18 | 7056205 | 7056205 |  | 3951472 | -7056205 | -100 | BID BV 774/2019 Profesional Services for the Construction of Swimming Pool at Zweletemba | Advertized 6 December 2019 | Time period for design and construction phase. | Fast track of procurement process, if posible. | Mr Steyn
10 | Esselen Park - Replacement of fence perimeter | 50101004531 | Town: All Wards: 1 to 21 | 4320000 | 4020000 |  | 2419200 | -4020000 | -100 | Planning phase completed done by the Consultant that was appointed, Delta Built Enviroment Consultants. The contruction process was advertised closing date was 19 July 2019. | The BEC is scheduled for 10 September 2019 and the BAC for 13 September 2019. | Project cancelled due to shortage of funding. Still waiting on feedback from CIDB to readvertise as soon as possible. | Project cancelled due to shortage of funding. Still waiting on feedback from CIDB to readvertise as soon as possible. | Mr Pienaar
Totals |  |  |  | 116116887 | 115816887 | 15634019.26 | 65025455 | -100182867.74 | -86.5011
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)