## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 31 July 2022
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Person
1 | Reservoirs: Pre-loads | 50101003091/ 50101003111 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 21 | 73481277 | 73481277 | 2766975.66 | 6500000 | -70714301.34 | -96.2344 | Construction | Construction | Hard rock | Heavy excavation machinery . | Mr Steyn
2 | Rawsonville WwTW: Extension of WwTW (0,24 Ml/day) | 50101003281 | Town: Rawsonville Wards: 19,20 | 27000000 | 27000000 |  | 2000000 | -27000000 | -100 | Construction | Construction | Ground water | Pumping og ground water . | Mr Steyn
3 | Transhex:Electrical Reticulation | 50101002431 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 1000000 | -15000000 | -100 | BV899/2021 already adjuducated. | Specification/Construction | N/A | N/A | Mr Beneke
4 | Upgrading of Sewer Network: External Loan | 50101003381 | Town: Worcester. Wards:5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 21 | 15000000 | 15000000 |  | 0 | -15000000 | -100 | Tender phase ( Tender close on 5 August 2022) | Tender phase ( Tender close on 5 August 2022) | None | N/A | Mr Pekeur
5 | Supply and Installation of Load Shedding Solution and Solar PV | 50101006481 | Town: All Wards: 1 to 21 | 13420000 | 13420000 |  | 0 | -13420000 | -100 | Awaiting assistance from SCM to capture request for tender to appoint Engineering Consultants to draft tender specifications | Preliminary study completet | Yes. No one can assist with capturing the request for the tender to appoint engineering consultant since 25 July 2022 | Constant follow-up | Mr Smal
6 | ICT - Computer Equipment | 50101004661 | Town: All Wards: 1 to 21 | 12000000 | 12000000 |  | 0 | -12000000 | -100 | Specifications submitted to SCU. | Specification | N/A | N/A | Mr Solomon
7 | Alternative Electricity Supply Zwelethemba | 50101002231 | Town: Worcester. Wards: 8, 16, 17, 18 | 10000000 | 10000000 |  | 0 | -10000000 | -100 | BV970/2022 Tender to be advitised closing date 02/09/2022 |  |  |  | Mr Beneke
8 | Altona new Electrical Substation | 50101002121 | Town: Worcester. Wards: 5 | 10000000 | 10000000 |  | 0 | -10000000 | -100 | BV900/2021 already adjudicated | Construction | N/A | N/A | Mr Beneke
9 | De Doorns Water Purification Works : Augmentation of DAF Unit (MIG funding) | 50101003201 | Town: De Doorns Wards: 2 | 7773398 | 7773398 |  | 0 | -7773398 | -100 | Preliminary investigation | Preliminary investigation | Project to be posponed until the 2023/2024 FY | Project to be posponed until the 2023/2024 FY | Mr Steyn
10 | 66KV Ripple Control | 50101002241 | Town: All Wards: 1 to 21 | 6900000 | 6900000 |  | 0 | -6900000 | -100 | BV973/2022 Tender in specification stage. |  |  |  | Mr Beneke
Totals |  |  |  | 190574675 | 190574675 | 2766975.66 | 9500000 | -187807699.34 | -98.5481
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)