## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 31 October 2019
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Official
1 | Worcester : Material Recovery Facility (MIG Counter funding) | 50101002651 | Town: Worcester. Wards: 5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 16979604 | 16979604 | 6680503.26 | 5263676 | -10299100.74 | -60.6557 | Construction commenced on 28 May 2019. | Construction | None to date. | N/A | Mr Steyn
2 | TRANSHEX - Water Reticulation | 50101002581 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 4650000 | -15000000 | -100 |  |  |  |  | Mr Mayeki
3 | TRANSHEX - Sewer Reticulation | 50101002601 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 4650000 | -15000000 | -100 |  |  |  |  | Mr Mayeki
4 | TRANSHEX - Roads | 50101002761 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 4650000 | -15000000 | -100 |  |  |  |  | Mr Mayeki
5 | TRANSHEX - Stormwater | 50101002921 | Town: Worcester. Wards: 18 | 15000000 | 15000000 |  | 4650000 | -15000000 | -100 |  |  |  |  | Mr Mayeki
6 | Pre-loads Reservoir | 50102154361 | Town: Worcester. Wards: 5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 10652819 | 10652819 |  | 3302375 | -10652819 | -100 | Draft specifications for the appointment of Consulting Engineers for the design and contract administration. | Specifications | Time period for design and construction phase. | Fast track of procurement process, if posible. | Mr Steyn
7 | Transhex : Electrical Reticulation | 50101002531 | Town: Worcester. Wards: 18 | 10000000 | 10000000 | 672117.91 | 3100000 | -9327882.09 | -93.2788 | Multi Year Tender BV 653 awarded to HVT. Contract in progress. (New Tender to be provided for Bulk Infrstructure) | Construction | N/A | N/A | Mr Beneke
8 | De Doorns Water Purification Works : Augmentation of DAF Unit | 50101003571 | Town: Worcester. Wards: 2 ,3,4 | 7108259 | 7108259 |  | 2203561 | -7108259 | -100 | Draft specifications for the appointment of Consulting Engineers for the design and contract administration. | Specifications | Time period for design and construction phase. | Fast track of procurement process, if posible. | Mr Steyn
9 | Zweletemba - New Swimming Bath | 50101004421 | Town: Worcester. Wards: 8, 16-18 | 7056205 | 7056205 |  | 2187422 | -7056205 | -100 | It was not necessary to appoint consultants for the EIA and feasibility study because we will make use of our own sportsground at Zwelethemba. The execution of this decision was subject to detailed internal assessments and community consultation which occurred after the amendment of the TL SDBIP during February 2019. | Specifications | Finalisation of location of swimming pool. Project Steering Committee should be in agreement. | Fast track of procurement process, if posible. | Mr Steyn
10 | Esselen Park - Replacement of fence perimeter | 50101004531 | Town: All Wards: 1 to 21 | 4320000 | 4020000 |  | 1339200 | -4020000 | -100 | Planning phase completed done by the Consultant that was appointed, Delta Built Enviroment Consultants. The contruction process was advertised closing date was 19 July 2019. | The BEC is scheduled for 10 September 2019 and the BAC for 13 September 2019. | Project cancelled due to shortage of funding. Still waiting on feedback from CIDB to readvertise as soon as possible. | Project cancelled due to shortage of funding. Still waiting on feedback from CIDB to readvertise as soon as possible. | Mr Pienaar
Totals |  |  |  | 116116887 | 115816887 | 7352621.17 | 35996234 | -108464265.83 | -93.6515
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)