## Creditors
Outstanding creditors: 30 days and older
Name of supplier | Outstanding Amount | Invoice(s) date(s) | Dispute/Reason for non-payment | Remedial action

## Capital Expenditure
Top 10 Capital Projects till 30 June 2019 (Preliminary)
Number | Project description |  | Locations | Original Budget R'000 | Adjusted budget R'000 | YTD Expenditure R'000 | SDBIP / YTD budget | Variance R'000 | Variance % | Status of the project | At what stage is each project currently | Any challenges identified that is resulting in delays? | What measures are in place to remedy the existing challenges. | Responsible Official
1 | Langerug Reservoir | 50102151081 | Town: Worcester. Wards: 5, 6,7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18 | 25370157 | 25370157 | 25087977.37 | 25370157 | -282179.63 | -1.1123 | Contract BV 593 for the construction of 20 Ml reservoir awarded to Murray & Dicson. Reservoir roof collapshed on 25 January 2019. Anticipated delay in completion approximately 2 months. Revised completion towards end of June 2019. | Construction | Hard rock excavation and rainfall during June / July 2018. The dome roof of the reservoir collapsed on Friday, 25 January 2019. roof to be reconstructed may coase a delay of two months. | Adjustment to programme where posible. | Mr Steyn
2 | Transhex Development : Stormwater | 50101004291 | Town: Worcester. Wards: 18 | 17500000 | 17500000 | 17667346.5 | 17500000 | 167346.5 | 0.95627 | Multi - year project Phase 1.1 (258) serviced site has been completed | Completed | N/A | N/A | Mr Mayeki
3 | Transhex Development : Roads | 50101004171 | Town: Worcester. Wards: 18 | 17500000 | 17500000 | 17667346.5 | 17500000 | 167346.5 | 0.95627 | Multi - year project Phase 1.1 (258) serviced site has been completed | Completed | N/A | N/A | Mr Mayeki
4 | Transhex Development : Sewer Reticulation | 50101003611 | Town: Worcester. Wards: 18 | 17500000 | 17500000 | 17667346.5 | 17500000 | 167346.5 | 0.95627 | Multi - year project Phase 1.1 (258) serviced site has been completed | Completed | N/A | N/A | Mr Mayeki
5 | Transhex Development : Water Reticulation | 50101003481 | Town: Worcester. Wards: 18 | 17500000 | 17500000 | 17667346.96 | 17500000 | 167346.96 | 0.95627 | Multi - year project Phase 1.1 (258) serviced site has been completed | Completed | N/A | N/A | Mr Mayeki
6 | Bulk Electrical: Worcester Transhex 7300 | 50101003401 | Town: Worcester. Wards: 18 | 13300000 | 13300000 | 3557542.25 | 13300000 | -9742457.75 | -73.2516 | Multy year Tender Bv 653 awarded. Contrac in progress | Construction | Contract for construction of houses delayed. To be rolled over and completed in 2019/20.Project outside control of BVM implemented by PAWC | N/A | Mr Beneke
7 | Sewer pumpstation and rising main | 50101003581 | Town: Worcester. Wards: 10 | 10000000 | 17793295 | 17764279.72 | 17793295 | -29015.28 | -0.16307 | Contract BV 596 for the construction of sewer pump station awarded to East coast irrigation. Due completion towards end of April 2019. | Completed | Rainfall during June / July 2018. | Adjustment to programme where posible. | Mr Steyn
8 | Zweletemba : New Swimming Bath | 50101004521 | Town: Worcester Wards: 1 to 21 | 7161405 | 100000 |  | 100000 | -100000 | -100 | Tender BV679 Proffesional Architechtural Services for Design and Feasability Study of the New Proposes Swimming Pool in Zwelethemba, Worcester . Advertisment Process will take place during next week (10 - 15 December 2018) | Tender | Procurement process | Appointment of project manager | Mr Pienaar
9 | Electricity : Cherry Picker vehicles x 10 | 50101003861 | Town: All Wards: 1 to 21 | 5450000 | 5020000 | 4859909.69 | 5020000 | -160090.31 | -3.189 | Final Invoice was submitted for Payment. | Completed | N/A | N/A | Mr Beneke
10 | IT : Infrastructure Replacement (Servers and Storage) | 50102151121 | Town: All Wards: 1 to 21 | 4800000 | 1082830 | 987264.45 | 1082830 | -95565.55 | -8.8255 | Installation, configuration and setup completed. Invoice outstanding | Completed | None | N/A | Mr Solomon
Totals |  |  |  | 136081562 | 132666282 | 122926359.94 | 132666282 | -9739922.06 | -7.3417
Project status: If the project is in the SCM process of being procured. Please state in which stage (planning, specification, advertising, etc)